## FRS
FUNCTIONAL REQUIREMENTS SPECIFICATION (FRS) — OpenCart Manual Testing Project
Application: demo.opencart.com ¦ Tester: Dhruv raj saxena ¦ Version: 1.1 ¦ Total Requirements: 28
Req ID | Module | Requirement Description
FR-001 | Registration | User should be able to register with valid First Name, Last Name, Email, and Password.
FR-002 | Registration | System should show an error message if any required field (First Name, Last Name, Email, Password) is left blank during registration.
FR-003 | Registration | System should not allow registration with an email that is already registered in the system.
FR-004 | Registration | User must check the Privacy Policy checkbox before clicking Continue. Registration should fail without it.
FR-005 | Registration | System should reject a password shorter than 4 characters (minimum length = 4).
FR-006 | Registration | System should reject a password longer than 20 characters (maximum length = 20).
FR-007 | Registration | System should reject invalid characters such as numbers or special characters in the First Name and Last Name fields.
FR-008 | Registration | System should hide the password characters using the '*' masking symbol while the user is typing in the Password field.
FR-009 | Login | User should be able to login using valid registered email and correct password.
FR-010 | Login | System should show an error message if the entered email or password is incorrect.
FR-011 | Login | System should show an error message if one or both login fields are left empty on submit.
FR-012 | Login | The 'Forgot Password' link on the login page should work and redirect the user to the password reset page.
FR-013 | Login | The Password field on the login page should mask characters with '*' while the user is typing.
FR-014 | Logout | A logged-in user should be able to logout from the application using the My Account menu.
FR-015 | Logout | After logout, pressing the browser Back button should NOT restore the session or take the user back to the account dashboard. The session must be fully cleared.
FR-016 | Logout | Users who are not logged in should not see the Logout option in the navigation menu.
FR-017 | Product | When a user clicks on a product card, it should open that product's detail page with all information (name, image, price, description, Add to Cart button).
FR-018 | Product | User should be able to add a product to the cart using the 'Add to Cart' button on both the product card and the product detail page.
FR-019 | Product | User should be able to add a product to the wishlist. Guest users should be prompted to login before the product is added.
FR-020 | Product | User should be able to add a product to the compare list using the Compare button on the product card or detail page.
FR-021 | Product | Product cards on the listing page should display correct information: image, title, description, and price. Cards should be consistent in layout and dimensions.
FR-022 | Cart | User should be able to see all products added to the cart with correct name, pricing, tax, and total amount.
FR-023 | Cart | When a user adds any product to the cart, the cart icon in the header should update to show the correct item count and total price.
FR-024 | Cart | User should be able to remove a product from the cart.
FR-025 | Cart | User should be able to change the quantity of a product in the cart and the total should update accordingly.
FR-026 | Cart | When the cart is empty, a message should be displayed and a 'Continue Shopping' button should redirect the user to the homepage.
FR-027 | Checkout | When the cart has items, the user should be able to proceed to the checkout page successfully.
FR-028 | Checkout | When the cart is empty, the Checkout button should not be accessible or should display an appropriate error.
FR-029 | Wishlist | The wishlist icon count in the header should update in real-time after a product is added to the wishlist by a logged-in user.

## Test Scenarios
TEST SCENARIOS — OpenCart Manual Testing Project
Scenario ID | Module | Scenario Description
TS-001 | Registration | Verify user can register with valid details
TS-002 | Registration | Verify error message is displayed when required fields are empty
TS-003 | Registration | Verify user must accept privacy policy before registration
TS-004 | Registration | Verify user cannot register with an already registered email
TS-005 | Registration | Verify password must meet minimum and maximum length requirements
TS-006 | Registration | Verify system rejects invalid characters (numbers/special chars) in name fields
TS-007 | Registration | Verify password field is masked on registration page
TS-008 | Login | Verify user can login with valid credentials
TS-009 | Login | Verify error message is displayed for invalid credentials
TS-010 | Login | Verify error message when login fields are empty
TS-011 | Login | Verify Forgot Password link redirects to reset password page
TS-012 | Login | Verify password field is masked on login page
TS-013 | Logout | Verify user can logout successfully
TS-014 | Logout | Verify logout option is not visible to non-logged-in users
TS-015 | Logout | Verify user session is terminated after logout and browser back button does not restore it
TS-016 | Product | Verify product card displays correct information (image, title, description, price)
TS-017 | Product | Verify user is redirected to product detail page on clicking product
TS-018 | Product | Verify user can add product to cart from listing and detail page
TS-019 | Product | Verify user can add product to wishlist (logged in and guest)
TS-020 | Product | Verify user can add product to compare list
TS-021 | Product | Verify product card UI elements and layout are consistent
TS-022 | Cart | Verify user is redirected to cart page on clicking cart button
TS-023 | Cart | Verify cart displays correct product details (name, price, quantity, total)
TS-024 | Cart | Verify user can remove product from cart
TS-025 | Cart | Verify user can update product quantity in cart
TS-026 | Cart | Verify total price updates correctly when quantity changes
TS-027 | Cart | Verify empty cart state shows message and Continue Shopping button
TS-028 | Checkout | Verify user can proceed to checkout with items in cart
TS-029 | Checkout | Verify checkout is not allowed when cart is empty
TS-030 | Wishlist | Verify wishlist icon count updates after adding a product

## Test Cases
TEST CASES — OpenCart Manual Testing Project
TC ID | Scenario ID | Module | Preconditions | Description | Test Steps | Expected Result | Priority | Actual Result | Status | Bug ID | Notes
TC-001 | TS-001 | Registration | User is on Registration page demo.opencart.com > My Account > Register | Register with valid credentials | 1. Enter First Name: Sunny 2. Enter Last Name: Deol 3. Enter Email: sunnydeol01@test.com 4. Enter Password: Test@123 5. Check Privacy Policy checkbox 6. Click Continue | Account created successfully. User redirected to success page: 'Your Account Has Been Created!' | High | Account created successfully. User redirected to success page: 'Your Account Has Been Created!' | Pass
TC-002 | TS-002 | Registration | User is on Registration page | Submit registration with First Name blank | 1. Leave First Name empty 2. Fill Last Name, Email, Password with valid data 3. Check Privacy Policy 4. Click Continue | Error: 'First Name must be between 1 and 32 characters!' Form is not submitted. | High | Error: 'First Name must be between 1 and 32 characters!' Form is not submitted. | Pass
TC-003 | TS-002 | Registration | User is on Registration page | Submit registration with Last Name blank | 1. Fill First Name 2. Leave Last Name empty 3. Fill Email, Password 4. Check Privacy Policy 5. Click Continue | Error: 'Last Name must be between 1 and 32 characters!' Form is not submitted. | High | Error: 'Last Name must be between 1 and 32 characters!' Form is not submitted. | Pass
TC-004 | TS-002 | Registration | User is on Registration page | Submit registration with Email field blank | 1. Fill First Name, Last Name, Password 2. Leave Email empty 3. Check Privacy Policy 4. Click Continue | Error: 'E-Mail Address does not appear to be valid!' Form is not submitted. | High | Error: 'E-Mail Address does not appear to be valid!' Form is not submitted. | Pass
TC-005 | TS-002 | Registration | User is on Registration page | Submit registration with Password field blank | 1. Fill First Name, Last Name, Email 2. Leave Password empty 3. Check Privacy Policy 4. Click Continue | Error: 'Password must be between 4 and 20 characters!' Form is not submitted. | High | Error: 'Password must be between 4 and 20 characters!' Form is not submitted. | Pass
TC-006 | TS-002 | Registration | User is on Registration page | Submit registration with all fields empty | 1. Leave all fields empty 2. Do NOT check Privacy Policy 3. Click Continue | All required field error messages displayed at once. Form is not submitted. | Medium | All required field error messages displayed at once. Form is not submitted. | Pass
TC-007 | TS-003 | Registration | User is on Registration page | Submit registration without checking Privacy Policy | 1. Fill all fields with valid data 2. Do NOT check Privacy Policy checkbox 3. Click Continue | Error: 'Warning: You must agree to the Privacy Policy!' Form is not submitted. | High | Error: 'Warning: You must agree to the Privacy Policy!' Form is not submitted. | Pass
TC-008 | TS-004 | Registration | Account with email sunnydeol01@test.com already exists | Submit registration using an already registered email | 1. Fill First Name: Jane, Last Name: Smith 2. Enter Email: sunnydeol01@test.com 3. Enter Password: Test@123 4. Check Privacy Policy 5. Click Continue | Error: 'Warning: E-Mail Address is already registered!' Account is not created. | High | Error: 'Warning: E-Mail Address is already registered!' Account is not created. | Pass
TC-009 | TS-005 | Registration | User is on Registration page | Register with password of 3 characters — below minimum boundary | 1. Fill First Name, Last Name, Email 2. Enter Password: abc (3 characters) 3. Check Privacy Policy 4. Click Continue | Error: 'Password must be between 4 and 20 characters!' Form is not submitted. | High | Error: 'Password must be between 4 and 20 characters!' Form is not submitted. | Pass
TC-010 | TS-005 | Registration | User is on Registration page | Register with password of exactly 4 characters — lower boundary | 1. Fill First Name, Last Name, Email 2. Enter Password: ab12 (exactly 4 characters) 3. Check Privacy Policy 4. Click Continue | Registration is successful. Password of exactly 4 characters is accepted. | High | Registration is successful. Password of exactly 4 characters is accepted. | Pass
TC-011 | TS-005 | Registration | User is on Registration page | Register with password of exactly 20 characters — upper boundary | 1. Fill First Name, Last Name, Email 2. Enter Password: TestPassword@12345 (exactly 20 characters) 3. Check Privacy Policy 4. Click Continue | Registration is successful. Password of exactly 20 characters is accepted as the maximum valid length. | High | — Execute on demo.opencart.com and record result — | Not Run |  | Upper boundary — must pass
TC-012 | TS-005 | Registration | User is on Registration page | Register with password of 21 characters — above maximum boundary | 1. Fill First Name, Last Name, Email 2. Enter Password: TestPassword@123456 (21 characters) 3. Check Privacy Policy 4. Click Continue | Error: 'Password must be between 4 and 20 characters!' Form is not submitted. | High | — Execute on demo.opencart.com and record result — | Not Run |  | Above maximum — must fail
TC-013 | TS-006 | Registration | User is on Registration page | Register with numbers in First Name field | 1. Enter First Name: John123 2. Fill Last Name, Email, Password 3. Check Privacy Policy 4. Click Continue | Error shown rejecting numbers in name field. Form is not submitted. | Medium | Account created. System accepted 'John123' as First Name — no validation error. | Fail | BUG-001
TC-014 | TS-006 | Registration | User is on Registration page | Register with special characters in First Name field | 1. Enter First Name: J@hn! 2. Fill Last Name, Email, Password 3. Check Privacy Policy 4. Click Continue | Error shown rejecting special characters in name field. Form is not submitted. | Medium | Account created. System accepted 'J@hn!' as First Name — no validation error. | Fail | BUG-002
TC-015 | TS-006 | Registration | User is on Registration page | Register with numbers in Last Name field | 1. Fill First Name 2. Enter Last Name: Doe456 3. Fill Email, Password 4. Check Privacy Policy 5. Click Continue | Error shown rejecting numbers in name field. Form is not submitted. | Medium | Account created. System accepted 'Doe456' as Last Name — no validation error. | Fail | BUG-003
TC-016 | TS-006 | Registration | User is on Registration page | Register with special characters in Last Name field | 1. Fill First Name 2. Enter Last Name: D#e$ 3. Fill Email, Password 4. Check Privacy Policy 5. Click Continue | Error shown rejecting special characters in name field. Form is not submitted. | Medium | Account created. System accepted 'D#e$' as Last Name — no validation error. | Fail | BUG-004
TC-017 | TS-007 | Registration | User is on Registration page | Verify password field is masked on Registration page | 1. Click on the Password field 2. Type any characters: Test@123 3. Observe characters on screen | Each character typed appears as * or bullet. Actual password is not visible. | Medium | Each character appears as *. Password is not visible on screen. | Pass
TC-018 | TS-008 | Login | Account: sunnydeol01@test.com ¦ Pass: Test@123 User is on Login page | Login with registered email and correct password | 1. Open Login page 2. Enter Email: sunnydeol01@test.com 3. Enter Password: Test@123 4. Click Login | User logged in. Redirected to My Account page. Dashboard is visible. | High | User logged in. Redirected to My Account page. Dashboard is visible. | Pass
TC-019 | TS-009 | Login | User is on Login page | Login with unregistered email | 1. Enter Email: notregistered001@test.com 2. Enter Password: Test@123 3. Click Login | Error: 'Warning: No match for E-Mail Address and/or Password.' | High | Error: 'Warning: No match for E-Mail Address and/or Password.' | Pass
TC-020 | TS-009 | Login | Account: sunnydeol01@test.com ¦ User is on Login page | Login with valid email but wrong password | 1. Enter Email: sunnydeol01@test.com 2. Enter Password: WrongPass999 3. Click Login | Error: 'Warning: No match for E-Mail Address and/or Password.' | High | Error: 'Warning: No match for E-Mail Address and/or Password.' | Pass
TC-021 | TS-010 | Login | User is on Login page | Login with blank email field but password filled | 1. Leave Email field empty 2. Enter Password: Test@123 3. Click Login | Error is displayed. Login does not proceed. | High | Error: 'Warning: No match for E-Mail Address and/or Password.' | Pass
TC-022 | TS-010 | Login | User is on Login page | Login with blank password field but email filled | 1. Enter Email: sunnydeol01@test.com 2. Leave Password empty 3. Click Login | Error is displayed. Login does not proceed. | High | Error: 'Warning: No match for E-Mail Address and/or Password.' | Pass
TC-023 | TS-011 | Login | User is on Login page | Click Forgot Password link on login page | 1. Observe the login page 2. Click 'Forgotten Password' link 3. Observe the page that loads | User redirected to Forgotten Password page. Email input field is visible. | Medium | User redirected to Forgotten Password page. Email input field is visible. | Pass
TC-024 | TS-012 | Login | User is on Login page | Verify password field is masked on login page | 1. Click on the Password field 2. Type any characters: Test@123 3. Observe characters on screen | Each character typed appears as * or bullet. Actual password is not visible. | Medium | Each character appears as *. Password is not visible on screen. | Pass
TC-025 | TS-013 | Logout | User is logged in as sunnydeol01@test.com | Verify logout functionality works properly | 1. Click 'My Account' in the top navigation 2. Click 'Logout' in the dropdown 3. Observe the page and header | User is logged out. Redirected to logout page. Header shows 'Login' and 'Register' instead of 'Logout'. | High | User is logged out. Header shows 'Login' and 'Register' instead of 'Logout'. | Pass
TC-026 | TS-014 | Logout | User is NOT logged in (guest user) | Verify Logout option is hidden for non-logged-in users | 1. Open demo.opencart.com without logging in 2. Click 'My Account' in top navigation 3. Observe the dropdown options | Dropdown shows only 'Register' and 'Login'. 'Logout' is NOT visible. | High | Dropdown shows only 'Register' and 'Login'. 'Logout' is NOT visible. | Pass
TC-027 | TS-015 | Logout | User was logged in and just successfully logged out | Press Back button after logout to check session is not restored | 1. After logout, confirm user is on logout page 2. Press browser Back button 3. Observe the page that loads | User is NOT taken back to account dashboard. Session is cleared. Login page is shown. | High | User NOT taken back to account dashboard. Session cleared. Login page shown. | Pass
TC-028 | TS-016 | Product | User is on homepage or any category listing page | Verify product card shows correct information | 1. Navigate to homepage 2. Observe Featured Products section 3. Check each product card | Each card shows: product image (not broken), title/name, short description, and price. | High | Each card shows: image, title, description, and price correctly. | Pass
TC-029 | TS-017 | Product | User is on homepage or category listing page | Click on product card to open product detail page | 1. Click on any product name or image 2. Observe the page that opens | User redirected to correct product detail page: name, price, image, description, Add to Cart, Wishlist, Compare. | High | User redirected to correct product detail page with all required information. | Pass
TC-030 | TS-018 | Product | User is on a product listing page or homepage | Add product to cart from product card (listing page) | 1. Locate any product card 2. Click 'Add to Cart' on the card 3. Observe notification and cart icon | Success notification shown. Cart icon updates to show correct item count and total. | High | Success notification shown. Cart icon updates correctly. | Pass
TC-031 | TS-018 | Product | User is on a product detail page | Add product to cart from product detail page | 1. Open any product detail page 2. Set Qty to 1 3. Click 'Add to Cart' 4. Observe notification and header | Success: 'You have added [product name] to your shopping cart!' Cart icon updates. | High | Success notification shown. Cart icon updates with correct count and total. | Pass
TC-032 | TS-018 | Product | User is on a product detail page | Add multiple quantity of same product from detail page | 1. Open any product detail page 2. Change Qty from 1 to 3 3. Click 'Add to Cart' 4. Observe cart icon | 3 units added. Cart icon shows correct count. Total reflects unit price × 3. | Medium | 3 units added. Cart icon shows correct count. Total is correct. | Pass
TC-033 | TS-019 | Product | User is logged in. User is on a product detail page. | Add product to wishlist when logged in | 1. Open any product detail page 2. Click the Wishlist icon/button 3. Observe the notification | Success: 'You have added [product name] to your wish list!' | Medium | Success message shown. Product appears in My Account > Wish List. | Pass
TC-034 | TS-019 | Product | User is NOT logged in. User is on a product detail page. | Add product to wishlist when logged out (guest) | 1. Without logging in, open any product detail page 2. Click the Wishlist icon/button 3. Observe what happens | User gets a popup/redirect to login. Product is not added until user logs in. | Medium | User gets a popup to login first. Product not added until logged in. | Pass
TC-035 | TS-020 | Product | User is on a product listing page or detail page | Add product to compare list using Compare button | 1. Click the 'Compare this Product' button on any product 2. Observe the notification | Notification: 'You have added [product name] to your product comparison!' | Low | Notification shown. Compare count updates. | Pass
TC-036 | TS-021 | Product | User is on any category listing page | Verify UI and layout consistency of product cards | 1. Navigate to any category page (e.g. Desktops > Show All) 2. Observe layout and design of product cards | All cards are properly aligned in a grid. Images not broken. Text does not overflow. Buttons visible and correctly positioned. | Low | Product cards have inconsistent heights depending on description length. Grid is uneven. | Fail | BUG-005
TC-037 | TS-022 | Cart | User is on homepage. Cart has at least 1 item. | Click cart button in header to go to cart page | 1. Add any product to cart 2. Click the cart icon in the top-right header 3. Observe what happens | User redirected to Shopping Cart page (/checkout/cart). Page loads with all added items. | High | User redirected to Shopping Cart page. Page loads correctly. | Pass
TC-038 | TS-022 | Cart | User is on any page. Cart starts empty. | Verify cart icon updates when items are added | 1. Note cart icon shows 0 items 2. Add any product to cart 3. Observe cart icon in header | Cart icon updates in real-time to show correct number of items. | High | Cart icon updates in real-time correctly. | Pass
TC-039 | TS-022 | Cart | User has added MacBook ($602.00) to the cart | Verify cart button shows correct total amount in header | 1. Add MacBook to cart 2. Observe cart button in the header 3. Check the total displayed | Cart button in the header displays the correct total amount. | Medium | Cart button displays correct total amount. | Pass
TC-040 | TS-023 | Cart | User has added at least 1 product to the cart | Verify products are visible on the cart page | 1. Add any product to cart 2. Navigate to Cart page 3. Observe items listed | All added products are visible. None missing or duplicated. | High | All added products visible on cart page. | Pass
TC-041 | TS-023 | Cart | User has added MacBook to cart. User is on Cart page. | Verify all product information is correct on cart page | 1. Add MacBook to cart 2. Open Cart page 3. Check all product info | Cart shows: image, name, model, quantity (1), unit price ($602.00), line total. Sub-Total, Eco Tax, VAT (20%), Grand Total are mathematically correct. | High | Cart shows all information correctly. Totals are mathematically correct. | Pass
TC-042 | TS-024 | Cart | User is on Cart page with at least 1 product | Remove a product from the cart | 1. Navigate to Cart page 2. Click Remove (X) button next to any product 3. Observe cart after removal | Product removed. All totals update correctly. If last item removed, empty cart message appears. | High | Product removed. Totals update correctly. | Pass
TC-043 | TS-025 | Cart | User is on Cart page with at least 1 product | Update quantity of a product on the cart page | 1. On Cart page, locate Qty field for any product 2. Change quantity from 1 to 3 3. Click Update button | Quantity updates to 3. Line total = unit price × 3. Sub-Total, Tax, Grand Total all recalculate. | High | Quantity updates. All totals recalculate correctly. | Pass
TC-044 | TS-026 | Cart | MacBook ($602.00) is in cart with quantity 1. | Verify total price updates correctly when quantity is changed | 1. Note current Grand Total 2. Change MacBook qty to 2 3. Click Update 4. Compare new Grand Total | Grand Total increases proportionally. New subtotal = $602.00 × 2 = $1204.00. All totals correct. | High | Grand Total increases correctly. New total = $1204.00 before tax. | Pass
TC-045 | TS-027 | Cart | User is on Cart page with an empty cart | Verify empty cart shows message and Continue Shopping goes to homepage | 1. Remove all products from cart 2. Observe empty cart state 3. Click 'Continue' button | Empty cart message visible. Continue button displayed. Clicking redirects to homepage. | Medium | Empty cart message visible. Continue button redirects to homepage. | Pass
TC-046 | TS-028 | Checkout | User has at least 1 product in cart. User is NOT logged in. | Checkout as a guest (not logged in) | 1. Add any product to cart 2. Go to Cart page 3. Click 'Checkout' button 4. Observe checkout options | Checkout page loads. Options shown: 'New Customer' (guest or register) and 'Returning Customer' (login). | High | Clicking Checkout redirects back to Cart page. Checkout flow does not load. | Fail | BUG-006
TC-047 | TS-028 | Checkout | User is logged in as sunnydeol01@test.com. At least 1 product in cart. | Checkout after logging in | 1. Login as sunnydeol01@test.com 2. Add any product to cart 3. Go to Cart page 4. Click 'Checkout' button | User proceeds to checkout flow. Billing/shipping address step is shown. | High | Products are out of stock. Checkout did not proceed. Out of stock error shown. | Fail | BUG-007
TC-048 | TS-029 | Checkout | User is on the Cart page. Cart is empty. | Verify checkout is not accessible when cart is empty | 1. Remove all items from the cart 2. Navigate to /checkout/cart 3. Look for a Checkout button | Checkout button not visible OR clicking it shows an error that cart is empty. | High | Clicking Checkout on empty cart redirects back to Cart page. No error message shown. | Fail | BUG-008
TC-049 | TS-030 | Wishlist | User is logged in. User is on a product detail page. | Verify wishlist icon count updates after adding a product | 1. Note wishlist icon count in header (should show 0) 2. Click Wishlist button on any product 3. Observe wishlist icon count in header | Wishlist icon count increases by 1 (e.g. 0 → 1) after adding a product. | Medium | Wishlist icon count remains at 0. Count does not update in real-time. | Fail | BUG-009

## Bug Report
BUG REPORT — OpenCart Manual Testing Project
Bug ID | TC ID | Module | Bug Title | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status
BUG-001 | TC-013 | Registration | System accepts numbers in First Name field — no validation error | 1. Open Registration page 2. Enter First Name: John123 3. Fill all other fields 4. Check Privacy Policy 5. Click Continue | System should reject numbers in name fields and display a validation error. | Account created with 'John123' as First Name. No validation error shown. | Medium | Medium | Open
BUG-002 | TC-014 | Registration | System accepts special characters in First Name field — no validation error | 1. Open Registration page 2. Enter First Name: J@hn! 3. Fill all other fields 4. Check Privacy Policy 5. Click Continue | System should reject special characters in name fields and display a validation error. | Account created with 'J@hn!' as First Name. No validation error shown. | Medium | Medium | Open
BUG-003 | TC-015 | Registration | System accepts numbers in Last Name field — no validation error | 1. Open Registration page 2. Fill First Name 3. Enter Last Name: Doe456 4. Fill Email, Password 5. Check Privacy Policy 6. Click Continue | System should reject numbers in name fields and display a validation error. | Account created with 'Doe456' as Last Name. No validation error shown. | Medium | Medium | Open
BUG-004 | TC-016 | Registration | System accepts special characters in Last Name field — no validation error | 1. Open Registration page 2. Fill First Name 3. Enter Last Name: D#e$ 4. Fill Email, Password 5. Check Privacy Policy 6. Click Continue | System should reject special characters in name fields and display a validation error. | Account created with 'D#e$' as Last Name. No validation error shown. | Medium | Medium | Open
BUG-005 | TC-036 | Product | Product cards have inconsistent heights on category listing page | 1. Navigate to any category page (e.g. Desktops > Show All) 2. Observe the layout of product cards in the grid | All product cards should be uniform in height and aligned in a consistent grid layout. | Product cards have different heights depending on description length, causing a misaligned grid. | Low | Low | Open
BUG-006 | TC-046 | Checkout | Clicking Checkout as guest redirects back to Cart page instead of loading checkout flow | 1. Add any product to cart (not logged in) 2. Navigate to Cart page 3. Click 'Checkout' button | Checkout page loads with 'New Customer' and 'Returning Customer' options. | Clicking Checkout redirects user back to Cart page. Checkout flow does not load. | High | High | Open
BUG-007 | TC-047 | Checkout | Checkout fails for logged-in user — out of stock error prevents proceeding | 1. Login as sunnydeol01@test.com 2. Add any product to cart 3. Go to Cart page 4. Click 'Checkout' button | User taken to checkout flow. Billing/shipping address step should be shown. | Checkout does not proceed. Out-of-stock error displayed. Cannot move to next step. | High | High | Open
BUG-008 | TC-048 | Checkout | Checkout button on empty cart redirects to Cart page instead of showing error | 1. Remove all items from cart 2. Navigate to /checkout/cart 3. Click the Checkout button | Checkout button not visible OR shows error that cart is empty. User cannot proceed. | Clicking Checkout on empty cart redirects back to Cart page. No error message shown. | High | High | Open
BUG-009 | TC-049 | Wishlist | Wishlist icon count in header does not update after adding a product | 1. Login as sunnydeol01@test.com 2. Note wishlist icon count in header (shows 0) 3. Open any product detail page 4. Click Wishlist button 5. Observe wishlist icon count in header | Wishlist icon count should increase by 1 (e.g. 0 → 1) after adding a product. | Wishlist icon count remains at 0 even after successfully adding a product. Does not update in real-time. | Medium | Medium | Open

## RTM
REQUIREMENT TRACEABILITY MATRIX (RTM) — OpenCart Manual Testing Project
Maps every Requirement → Test Scenario → Test Case to ensure 100% coverage
Req ID | Module | Requirement Description | Scenario ID | Test Case IDs | Coverage
FR-001 | Registration | User can register with valid fields | TS-001 | TC-001 | ✔ Covered
FR-002 | Registration | Error shown when required fields are blank | TS-002 | TC-002, TC-003, TC-004, TC-005, TC-006 | ✔ Covered
FR-003 | Registration | Duplicate email not allowed | TS-004 | TC-008 | ✔ Covered
FR-004 | Registration | Privacy Policy checkbox mandatory | TS-003 | TC-007 | ✔ Covered
FR-005 | Registration | Password minimum length = 4 chars | TS-005 | TC-009, TC-010 | ✔ Covered
FR-006 | Registration | Password maximum length = 20 chars | TS-005 | TC-011, TC-012 | ✔ Covered
FR-007 | Registration | Invalid chars rejected in name fields | TS-006 | TC-013, TC-014, TC-015, TC-016 | ✔ Covered
FR-008 | Registration | Password masked on registration page | TS-007 | TC-017 | ✔ Covered
FR-009 | Login | Login with valid credentials | TS-008 | TC-018 | ✔ Covered
FR-010 | Login | Error on invalid email or password | TS-009 | TC-019, TC-020 | ✔ Covered
FR-011 | Login | Error on blank login fields | TS-010 | TC-021, TC-022 | ✔ Covered
FR-012 | Login | Forgot Password link works | TS-011 | TC-023 | ✔ Covered
FR-013 | Login | Password masked on login page | TS-012 | TC-024 | ✔ Covered
FR-014 | Logout | Logged-in user can logout | TS-013 | TC-025 | ✔ Covered
FR-015 | Logout | Back button after logout does not restore session | TS-015 | TC-027 | ✔ Covered
FR-016 | Logout | Logout not visible to guest users | TS-014 | TC-026 | ✔ Covered
FR-017 | Product | Clicking product card opens detail page | TS-017 | TC-029 | ✔ Covered
FR-018 | Product | Add to Cart from listing and detail page | TS-018 | TC-030, TC-031, TC-032 | ✔ Covered
FR-019 | Product | Wishlist — guest redirected to login | TS-019 | TC-033, TC-034 | ✔ Covered
FR-020 | Product | Compare button adds product to compare list | TS-020 | TC-035 | ✔ Covered
FR-021 | Product | Product card shows correct info and consistent layout | TS-016, TS-021 | TC-028, TC-036 | ✔ Covered
FR-022 | Cart | Cart shows correct products with pricing and totals | TS-023 | TC-040, TC-041 | ✔ Covered
FR-023 | Cart | Cart icon updates when item is added | TS-022 | TC-037, TC-038, TC-039 | ✔ Covered
FR-024 | Cart | User can remove product from cart | TS-024 | TC-042 | ✔ Covered
FR-025 | Cart | User can update quantity and total recalculates | TS-025, TS-026 | TC-043, TC-044 | ✔ Covered
FR-026 | Cart | Empty cart shows message and Continue Shopping | TS-027 | TC-045 | ✔ Covered
FR-027 | Checkout | Checkout works when cart has items | TS-028 | TC-046, TC-047 | ✔ Covered
FR-028 | Checkout | Checkout blocked when cart is empty | TS-029 | TC-048 | ✔ Covered
FR-029 | Wishlist | Wishlist icon count updates in real-time | TS-030 | TC-049 | ✔ Covered

## Test Summary
TEST SUMMARY REPORT & SIGN-OFF — OpenCart Manual Testing Project
Project Name |  | OpenCart Manual Testing Portfolio Project
Application URL |  | demo.opencart.com
Test Cycle |  | Cycle 1 — Functional Testing
Modules Tested |  | Registration ¦ Login ¦ Logout ¦ Product ¦ Cart ¦ Checkout ¦ Wishlist
Total Requirements |  | 29 (FR-001 to FR-029)
Prepared By |  | Dhruv Raj Saxena
Test Period |  | 30-04-2026 to 05-05-2026
Browser / OS |  | Google Chrome ¦ Windows 11
EXECUTION METRICS
Total Test Cases Planned |  |  | 49
Total Test Cases Executed |  |  | 47
Passed |  |  | 38
Failed |  |  | 9
Blocked |  |  | 0
Not Run (TC-011, TC-012) |  |  | 2
Pass Rate (of planned) |  |  | 77.55%
Fail Rate (of planned) |  |  | 18.37%
MODULE-WISE BREAKDOWN
Module | Total TCs | Passed | Failed | Pass Rate | Status
Registration | 17 | 11 | 4 | 64.7% | Partial
Login | 7 | 7 | 0 | 100% | Clear
Logout | 3 | 3 | 0 | 100% | Clear
Product | 9 | 8 | 1 | 88.9% | Partial
Cart | 9 | 9 | 0 | 100% | Clear
Checkout | 3 | 0 | 3 | 0% | Blocked
Wishlist | 1 | 0 | 1 | 0% | Blocked
BUG SUMMARY
Severity | Count | Bug IDs | Module | Status | Risk
Critical | 0 | — | — | — | None
High | 3 | BUG-006, BUG-007, BUG-008 | Checkout | Open | Release Blocker
Medium | 5 | BUG-001, BUG-002, BUG-003, BUG-004, BUG-009 | Registration, Wishlist | Open | Fix before release
Low | 1 | BUG-005 | Product | Open | Fix in next sprint
KEY OBSERVATIONS
✅ PASS | Login, Logout, and Cart modules passed 100%. All core user flows are functional.
✅ PASS | Registration positive flow works. Valid registration, blank field errors, duplicate email, and privacy policy validation all work correctly.
⚠️ BUG | Registration accepts numbers and special characters in First Name and Last Name (BUG-001 to BUG-004). No input validation on name fields. Needs fix before release.
🔴 HIGH | Checkout is completely blocked. Clicking Checkout as guest or logged-in user does not load the checkout flow (BUG-006, BUG-007). This is a RELEASE BLOCKER.
🔴 HIGH | Empty cart checkout not handled correctly. Checkout button on empty cart redirects to Cart page with no error message (BUG-008).
⚠️ BUG | Wishlist icon count in header does not update after adding a product (BUG-009). User has no real-time visual feedback.
ℹ️ NOTE | TC-011 (exactly 20 chars) and TC-012 (21 chars) are marked Not Run. Execute these on demo.opencart.com and update Actual Result and Status.
ℹ️ NOTE | RTM has been added to this project (Sheet 5). All 29 FRs are mapped to their Scenarios and Test Cases. Coverage = 100%.
FINAL QA DECISION
❌ NOT RECOMMENDED FOR RELEASE
Reason: 3 High severity bugs remain open in the Checkout module (BUG-006, BUG-007, BUG-008). The Checkout flow is completely non-functional — users cannot complete a purchase as a guest or logged-in user. All High severity bugs must be resolved and retested before sign-off. QA also recommends fixing Registration name field validation (BUG-001 to BUG-004) and Wishlist count (BUG-009). A full regression run of all 49 test cases is required after fixes are applied.
SIGN-OFF
Role | Name | Signature | Date | Decision | Comments
QA Engineer | Dhruv Raj Saxena | dhruv | 2026-05-06 | Pending | Awaiting bug fixes
QA Lead | [QA Lead Name] | ____________ | — | Pending | Review after retest
Dev Lead | [Dev Name] | ____________ | — | Pending | Fixes in progress
Product Owner | [PO Name] | ____________ | — | Pending | Blocked on checkout bugs